## Plan
Plan ID | Plan name | Date of export
GvWb9M3ouEuVfelLy4Yd2sgAAdgq | Week 4 - project : Team 73 | 2026-08-16

## Consolidated Data
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
5UIVD11gPUGTYuzvMBnNX8gAL3mG | Labels | Documents & Updates |  | Not started | Medium |  | Casper Shilo | 2026-08-09 |  |  |  | false
WxQofMSiNkm_rztVTNJqZMgAH237 | [BOOTSTRAP RESTYLING] -Write requirements for team page + login styling : 60 | Done |  | Completed | Important | Bevin Chathely;Casper Shilo | Casper Shilo | 2026-08-09 |  |  |  | false | 2026-08-16 | Casper Shilo | 5/5 | Login scope explicitly stated as styling-only;Team page fields listed with validation/display rules;Requirements shared with PM and UX;Document updated;Edge cases documented | BA;Sprint 1 | Description Determine the content fields for the team page (name, photo, role, blurb) and confirm the login work is styling only, with no changes to existing auth logic or session behavior. Document edge cases such as missing photos or long blurb text. Update Everything on Sprint 0 Master Document.docx
cMXlHtWyPkKJ18n1ADFf-cgABJBR | [BOOTSTRAP RESTYLING] Design Login Style & Team Page Layout :120 | Done |  | Completed | Medium | Casper Shilo;Asbi Babu | Casper Shilo | 2026-08-09 |  | 2026-08-12 |  | false | 2026-08-16 | Casper Shilo | 5/5 | Visual consistency between the two checked;Login page mockup complete;Design shared with BA for validation;Document Updated;Team page mockup complete | UX;Sprint 1 | Produce a mockup/wireframe of the restyled login page and a separate mockup of the team page layout, based on the BA's requirements document. Both must be visually consistent with each other. Update Task Document: Sprint 0 Master Document.docx
hIY1PL9NKUG9-0_XBbolKMgANVH8 | [BOOTSTRAP RESTYLING]- Validate Design Against Requirements : 60 | Done |  | Completed | Medium | Bevin Chathely;Casper Shilo | Casper Shilo | 2026-08-09 |  |  |  | false | 2026-08-16 | Casper Shilo | 5/5 | Design formally approved;Gaps (if any) sent back to UX and resolved;Document Updated;Login scope confirmed unchanged;Every required field checked against the design | BA;Sprint 1 | Check the UX mockups against the requirements document. Confirm every field is represented, the login mockup stays styling-only, and edge cases have a visible design treatment. Flag any gaps back to UX before approving. Update Sprint 0 Master Document.docx
NdK0vZEQd0OteYu_axqMJMgANRMh | [BOOTSTRAP RESTYLING]- Apply the approved visual design to the existing login page in the boilerplate. Do not modify the authentication logic, validation, or session handling — styling changes only : 60 | Done |  | Completed | Medium | Casper Shilo;Jesse Lang | Casper Shilo | 2026-08-09 |  |  |  | false | 2026-08-16 | Casper Shilo | 4/4 | Update document;Visual style matches approved mockup;Existing login validation/errors still function as before;No authentication logic changed | DEV;Sprint 1 | Apply the approved visual design to the existing login page in the boilerplate. Do not modify the authentication logic, validation, or session handling — styling changes only. update Sprint 0 Master Document.docx
KdwzS5O_EUWyzlYuNISMzcgAGrHO | [BOOTSTRAP RESTYLING]- Build Team Page & Auth Redirect : 120 | Done |  | Completed | Medium | Casper Shilo;Jesse Lang | Casper Shilo | 2026-08-09 |  |  |  | false | 2026-08-16 | Casper Shilo | 4/4 | Team page not directly accessible without login;Team page renders per design with all required fields;Successful login redirects to team page;Document updated | DEV;Sprint 1 | Build the team page per the approved design (name, member cards, blurb) and wire it so a successful login redirects the user here. The team page itself should not be reachable without a valid login. Update Doc: Sprint 0 Master Document.docx
8mTa4vDdBUGV9Ab3azvpb8gACYpn | [BOOTSTRAP RESTYLING] - Deploy - 120 | Done |  | Completed | Medium | Casper Shilo;Jesse Lang | Casper Shilo | 2026-08-09 |  |  |  | false | 2026-08-16 | Casper Shilo | 4/4 | Deployment completed via boilerplate pipeline;Live URL loads without errors;Login → redirect → team page flow spot-checked on the deployed URL;Document updated | DEV;Sprint 1 | Deploy the updated application (restyled login + team page + redirect) using the boilerplate's deployment pipeline. Confirm the deployed version is live and functioning before handing off to Dev 2. Update Doc: Sprint 0 Master Document.docx
ywUC8Zdqj0KxynwaJMd2XsgAOIMF | [BOOTSTRAP RESTYLING] Test Login → Redirect → Team Page Flow : 60 | Done |  | Completed | Medium | Casper Shilo;Daniel Granville | Casper Shilo | 2026-08-09 |  |  |  | false | 2026-08-16 | Casper Shilo | 4/4 | Document updated;Redirect to team page confirmed;All required content verified correct and complete;Valid login tested end-to-end on deployed URL | DEV;Sprint 1 | On the deployed URL (not localhost if possible) , test the full happy-path flow: valid login, redirect to team page, and all required content displaying correctly. Must not be the same dev who built this feature. Update Document: Sprint 0 Master Document.docx
9aTRX1fUrEaWBPtMffxJFsgAK6Kh | [BOOTSTRAP RESTYLING] - Test Edge Cases & Log Bugs : 60 | Done |  | Completed | Medium | Casper Shilo;Daniel Granville | Casper Shilo | 2026-08-09 |  |  |  | false | 2026-08-16 | Casper Shilo | 5/5 | Direct team-page access without login tested (must redirect);Invalid login tested;Missing-photo and long-blurb edge cases tested;Bugs logged with repro steps, or none-found confirmed;Update Document | DEV;Sprint 1 | Test edge cases identified by the BA: invalid login, direct team-page access without logging in, a missing photo, and an unusually long blurb. Log any bugs found back to Dev 1 with reproduction steps. Update Doc: Sprint 0 Master Document.docx
1RLdh4F2_E62GEe5-MSBr8gAMp9S | [BOOTSTRAP RESTYLING] - Final Review & Sign-Off : 30 | Done |  | Completed | Medium | Casper Shilo | Casper Shilo | 2026-08-09 | 2026-08-16 | 2026-08-16 |  | false | 2026-08-16 | Casper Shilo | 3/3 | Task moved to Done;All prior tasks' checklists verified complete;Feature reviewed end-to-end against requirements and design | PM;Sprint 1 | PM reviews the completed feature end-to-end against the original requirements and design, confirms every prior task's checklist is complete, and signs off. Document is finalized ande signed off

## Tasks
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
5UIVD11gPUGTYuzvMBnNX8gAL3mG | Labels | Al-rDcwWyEqq7uRreLThpMgALWjB |  | Not started | Medium |  | 770bfebb-fe9c-44c2-bd6d-62bc552ee562 | 2026-08-09 |  |  |  | false
WxQofMSiNkm_rztVTNJqZMgAH237 | [BOOTSTRAP RESTYLING] -Write requirements for team page + login styling : 60 | sIPTa4YgAE6FHiwsqcEnTMgAPA6s |  | Completed | Important | 30bf26fd-d272-4694-8c98-65747ec34485;770bfebb-fe9c-44c2-bd6d-62bc552ee562 | 770bfebb-fe9c-44c2-bd6d-62bc552ee562 | 2026-08-09 |  |  |  | false | 2026-08-16 | 770bfebb-fe9c-44c2-bd6d-62bc552ee562 | 5/5 | Login scope explicitly stated as styling-only;Team page fields listed with validation/display rules;Requirements shared with PM and UX;Document updated;Edge cases documented | BA;Sprint 1 | Description Determine the content fields for the team page (name, photo, role, blurb) and confirm the login work is styling only, with no changes to existing auth logic or session behavior. Document edge cases such as missing photos or long blurb text. Update Everything on Sprint 0 Master Document.docx
cMXlHtWyPkKJ18n1ADFf-cgABJBR | [BOOTSTRAP RESTYLING] Design Login Style & Team Page Layout :120 | sIPTa4YgAE6FHiwsqcEnTMgAPA6s |  | Completed | Medium | 770bfebb-fe9c-44c2-bd6d-62bc552ee562;37012735-20ce-43d2-a08b-38bef53ee3bf | 770bfebb-fe9c-44c2-bd6d-62bc552ee562 | 2026-08-09 |  | 2026-08-12 |  | false | 2026-08-16 | 770bfebb-fe9c-44c2-bd6d-62bc552ee562 | 5/5 | Visual consistency between the two checked;Login page mockup complete;Design shared with BA for validation;Document Updated;Team page mockup complete | UX;Sprint 1 | Produce a mockup/wireframe of the restyled login page and a separate mockup of the team page layout, based on the BA's requirements document. Both must be visually consistent with each other. Update Task Document: Sprint 0 Master Document.docx
hIY1PL9NKUG9-0_XBbolKMgANVH8 | [BOOTSTRAP RESTYLING]- Validate Design Against Requirements : 60 | sIPTa4YgAE6FHiwsqcEnTMgAPA6s |  | Completed | Medium | 30bf26fd-d272-4694-8c98-65747ec34485;770bfebb-fe9c-44c2-bd6d-62bc552ee562 | 770bfebb-fe9c-44c2-bd6d-62bc552ee562 | 2026-08-09 |  |  |  | false | 2026-08-16 | 770bfebb-fe9c-44c2-bd6d-62bc552ee562 | 5/5 | Design formally approved;Gaps (if any) sent back to UX and resolved;Document Updated;Login scope confirmed unchanged;Every required field checked against the design | BA;Sprint 1 | Check the UX mockups against the requirements document. Confirm every field is represented, the login mockup stays styling-only, and edge cases have a visible design treatment. Flag any gaps back to UX before approving. Update Sprint 0 Master Document.docx
NdK0vZEQd0OteYu_axqMJMgANRMh | [BOOTSTRAP RESTYLING]- Apply the approved visual design to the existing login page in the boilerplate. Do not modify the authentication logic, validation, or session handling — styling changes only : 60 | sIPTa4YgAE6FHiwsqcEnTMgAPA6s |  | Completed | Medium | 770bfebb-fe9c-44c2-bd6d-62bc552ee562;7630d330-58bf-479d-9852-7349e54f50d0 | 770bfebb-fe9c-44c2-bd6d-62bc552ee562 | 2026-08-09 |  |  |  | false | 2026-08-16 | 770bfebb-fe9c-44c2-bd6d-62bc552ee562 | 4/4 | Update document;Visual style matches approved mockup;Existing login validation/errors still function as before;No authentication logic changed | DEV;Sprint 1 | Apply the approved visual design to the existing login page in the boilerplate. Do not modify the authentication logic, validation, or session handling — styling changes only. update Sprint 0 Master Document.docx
KdwzS5O_EUWyzlYuNISMzcgAGrHO | [BOOTSTRAP RESTYLING]- Build Team Page & Auth Redirect : 120 | sIPTa4YgAE6FHiwsqcEnTMgAPA6s |  | Completed | Medium | 770bfebb-fe9c-44c2-bd6d-62bc552ee562;7630d330-58bf-479d-9852-7349e54f50d0 | 770bfebb-fe9c-44c2-bd6d-62bc552ee562 | 2026-08-09 |  |  |  | false | 2026-08-16 | 770bfebb-fe9c-44c2-bd6d-62bc552ee562 | 4/4 | Team page not directly accessible without login;Team page renders per design with all required fields;Successful login redirects to team page;Document updated | DEV;Sprint 1 | Build the team page per the approved design (name, member cards, blurb) and wire it so a successful login redirects the user here. The team page itself should not be reachable without a valid login. Update Doc: Sprint 0 Master Document.docx
8mTa4vDdBUGV9Ab3azvpb8gACYpn | [BOOTSTRAP RESTYLING] - Deploy - 120 | sIPTa4YgAE6FHiwsqcEnTMgAPA6s |  | Completed | Medium | 770bfebb-fe9c-44c2-bd6d-62bc552ee562;7630d330-58bf-479d-9852-7349e54f50d0 | 770bfebb-fe9c-44c2-bd6d-62bc552ee562 | 2026-08-09 |  |  |  | false | 2026-08-16 | 770bfebb-fe9c-44c2-bd6d-62bc552ee562 | 4/4 | Deployment completed via boilerplate pipeline;Live URL loads without errors;Login → redirect → team page flow spot-checked on the deployed URL;Document updated | DEV;Sprint 1 | Deploy the updated application (restyled login + team page + redirect) using the boilerplate's deployment pipeline. Confirm the deployed version is live and functioning before handing off to Dev 2. Update Doc: Sprint 0 Master Document.docx
ywUC8Zdqj0KxynwaJMd2XsgAOIMF | [BOOTSTRAP RESTYLING] Test Login → Redirect → Team Page Flow : 60 | sIPTa4YgAE6FHiwsqcEnTMgAPA6s |  | Completed | Medium | 770bfebb-fe9c-44c2-bd6d-62bc552ee562;e3ad5991-d204-41e1-bdb4-4c57281e7b92 | 770bfebb-fe9c-44c2-bd6d-62bc552ee562 | 2026-08-09 |  |  |  | false | 2026-08-16 | 770bfebb-fe9c-44c2-bd6d-62bc552ee562 | 4/4 | Document updated;Redirect to team page confirmed;All required content verified correct and complete;Valid login tested end-to-end on deployed URL | DEV;Sprint 1 | On the deployed URL (not localhost if possible) , test the full happy-path flow: valid login, redirect to team page, and all required content displaying correctly. Must not be the same dev who built this feature. Update Document: Sprint 0 Master Document.docx
9aTRX1fUrEaWBPtMffxJFsgAK6Kh | [BOOTSTRAP RESTYLING] - Test Edge Cases & Log Bugs : 60 | sIPTa4YgAE6FHiwsqcEnTMgAPA6s |  | Completed | Medium | 770bfebb-fe9c-44c2-bd6d-62bc552ee562;e3ad5991-d204-41e1-bdb4-4c57281e7b92 | 770bfebb-fe9c-44c2-bd6d-62bc552ee562 | 2026-08-09 |  |  |  | false | 2026-08-16 | 770bfebb-fe9c-44c2-bd6d-62bc552ee562 | 5/5 | Direct team-page access without login tested (must redirect);Invalid login tested;Missing-photo and long-blurb edge cases tested;Bugs logged with repro steps, or none-found confirmed;Update Document | DEV;Sprint 1 | Test edge cases identified by the BA: invalid login, direct team-page access without logging in, a missing photo, and an unusually long blurb. Log any bugs found back to Dev 1 with reproduction steps. Update Doc: Sprint 0 Master Document.docx
1RLdh4F2_E62GEe5-MSBr8gAMp9S | [BOOTSTRAP RESTYLING] - Final Review & Sign-Off : 30 | sIPTa4YgAE6FHiwsqcEnTMgAPA6s |  | Completed | Medium | 770bfebb-fe9c-44c2-bd6d-62bc552ee562 | 770bfebb-fe9c-44c2-bd6d-62bc552ee562 | 2026-08-09 | 2026-08-16 | 2026-08-16 |  | false | 2026-08-16 | 770bfebb-fe9c-44c2-bd6d-62bc552ee562 | 3/3 | Task moved to Done;All prior tasks' checklists verified complete;Feature reviewed end-to-end against requirements and design | PM;Sprint 1 | PM reviews the completed feature end-to-end against the original requirements and design, confirms every prior task's checklist is complete, and signs off. Document is finalized ande signed off

## Goals
Goal ID | Goal name | Status | Priority | Start date | Finish date | Connected tasks | Notes

## Buckets
Bucket ID | Bucket Name
TfMsbUkPFkis4qr3QFO-W8gALAxH | Blocked
Al-rDcwWyEqq7uRreLThpMgALWjB | Documents & Updates
CKXXfrMBWk2iGLZXfFuARMgAMtKc | Backlog
smyiTLoHQU2sCnICQ3EtsMgAOfdT | Doing
IXEU5UNn0EOwpOeMBarTg8gAAKxf | Reviewing
sIPTa4YgAE6FHiwsqcEnTMgAPA6s | Done
KRj0lW8dvUKmglCKODvx48gAHG0m | Testing
8BYSgfqkgUeR6akO4xjZ08gAA1n8 | Done
pLAqpTDMf0Kqa6KKNtPWj8gAOZjL | Clean up

## Users
User ID | User Name | Email
770bfebb-fe9c-44c2-bd6d-62bc552ee562 | Casper Shilo | s4008936@student.rmit.edu.au
30bf26fd-d272-4694-8c98-65747ec34485 | Bevin Chathely | S4092723@student.rmit.edu.au
37012735-20ce-43d2-a08b-38bef53ee3bf | Asbi Babu | S4075945@student.rmit.edu.au
7630d330-58bf-479d-9852-7349e54f50d0 | Jesse Lang | s4002576@student.rmit.edu.au
e3ad5991-d204-41e1-bdb4-4c57281e7b92 | Daniel Granville | s4004791@student.rmit.edu.au